## Master Event Checklist
Task Assignment | Task Deadline | Category | Description | Completed | (sort order)
|  | Event Conceptualization | Meet with university partners to brainstorm and pre-plan (purpose, outcome, goal, audience, location, date, time) |  | 1
|  | Event Conceptualization | If president is part of the event complete the "Request for President's Attendance" form and send to Chief of Staff in the VP for Advancement Office |  | 1
|  | Event Conceptualization | Check availability of event space and reserve rooms needed (on or off campus) |  | 1
|  | Event Conceptualization | Review "Master Event Sheet Question" template form within unit; update per meeting and review with unit leaders as necessary (see template) |  | 1
|  | Event Conceptualization | Develop event checklist (using the updated Master Event Sheet Question form) establishing assignments, deadlines, categories, descriptions (this document) |  | 1
|  | Event Conceptualization | Estimate expenses and identify funding source (see budget template) |  | 1
|  | Event Conceptualization | Meet with university partners to develop event program content and program flow (see program flow template) |  | 1
|  | Event Conceptualization | Determine marketing/communications needs using Mar/Com plan template and meet with Mar/Com team when applicable to brainstorm (see MarCom template) |  | 1
|  | Event Conceptualization | Confirm with UI administrators, faculty, staff, special guests, and speakers that the proposed date is on their calendars |  | 1
|  | Budget | Determine budget for event and develop budget tracking document by expense line. Update as each item is expensed to track expenses (see template) |  | 2
|  | Budget | If using a budget not within your department, work with fiscal person in that unit to determine budget protocol |  | 2
|  | Budget | Pay invoices as received and copy each expense item for the event's budget folder |  | 2
|  | Invitations | Use Argos for any portion of the lists it can provide for pre-determined audience; complete Advancement Services on-line request to order mailing list from Argos reports. Note: mailing lists are generally received within 24 hrs. If you do not have access to Argos request the lists using the on-line request form. Note: allow 2 weeks for processing |  | 3
|  | Invitations | Develop save the date copy (if applicable) and send to Creative Services to design (HTML email or print). If president's name is on the save the date review proof with Kevin Ketchie in the president's office. |  | 3
|  | Invitations | Develop invitation copy and send to Creative Services to design (HTML email or print). If president's name is on the invitation review proof with events manager in the president's office. Send final invitation copy and invitation list to the president's executive assistant |  | 3
|  | Invitations | Protocol states that the President extends all invitations on behalf of the university to the Governor. Contact events manager in the president's office to coordinate |  | 3
|  | Invitations | If invitation is emailed, work with unit web coordinator to send bulk email |  | 3
|  | Invitations | If invitation is mailed, work with Campus Mail to determine best method to mail (first class, bulk, etc.) They can address envelope as well as stamp and seal and in some cased stuff contents in envelope |  | 3
|  | RSVP | Establish how RSVP's will be accepted (phone, email, online, returned pre-printed card) |  | 4
|  | RSVP | If RSVPs are taken on-line, create event on UIRSVP site to accept RSVP's and payments (see link to instructions for setting event up) |  | 4
|  | RSVP | Create a spreadsheet of invited guests to log RSVP's (turn invitation list in to RSVP list) |  | 4
|  | RSVP | Post and maintain RSVP list on advancement shared drive in event RSVP list folder |  | 4
|  | RSVP | Send email to development officers and VP advising RSVP list has been posted to shared drive |  | 4
|  | RSVP | Send email to Prospect Research office to prepare bios following RSVPs on RSVP list; request draft 7 days prior to event and final day prior to event for leadership briefings |  | 4
|  | RSVP | Create RSVP confirmation letter and/or email including any pertinent information (date, time, place, dress, maps, transportation and parking info, etc.) and send via email or USPS |  | 4
|  | RSVP | If receiving payments via check prior, deposit to student accounts on a regular basis using GRT form. Copy checks before depositing and submit with adding machine tape with amounts |  | 4
|  | RSVP | Prior to starting seating chart and printing name tags, place cards, etc., confirm that all RSVPs are recorded correctly by double-checking against all RSVP mechanisms (UIRSVP, emails, phone calls, printed cards returned, etc.) |  | 4
|  | Program | Establish with the university partners if a program (emcee(s)/speaking/announcements/presentation/entertainment) will be part of the event |  | 5
|  | Program | Develop program flow (see sample) |  | 5
|  | Program | Extend invitation(s) to emcees, presenters, speakers, entertainment etc. |  | 5
|  | Program | Determine travel and accommodation needs for any program participants and make appropriate arrangements |  | 5
|  | Program | Identify, interview, and select emcee(s) |  | 5
|  | Program | Discuss and confirm set up needs with all participants |  | 5
|  | Program | Write program script for emcee(s) and other program participants (except president--see below) |  | 5
|  | Program | Notify and ask for talking points for the President from the Executive Communications Manager in the president's office. Helpful information: event title, date, time, location, purpose, outcome, goal, attendees, speaking length and topic, introductions and acknowledgements--attach program flow |  | 5
|  | Program | Schedule script read through with emcee(s) several days prior to event (not at venue)--update script as necessary |  | 5
|  | Program | Schedule walkthroughs/rehearsals with all participants on day of event |  | 5
|  | Program | Schedule sound check with Sound Production and Lighting and the emcee and speaker(s) on day of event |  | 5
|  | Program | Select video(s) to support program or have produced through Video Production |  | 5
|  | Guest hosting | Verify if there will be guests with special needs, i.e., sign language interpretee, special parking reserved, dietary considerations, etc. If special plans are needed to accommodate these guests, make these arrangements prior to the event |  | 6
|  | Guest hosting | Secure hotel block for out of town guests. Work with Purchasing and Contract Services on signing of contract(s) |  | 6
|  | Guest hosting | Coordinate welcome gift baskets and/or information packets be coordinated for guests, speakers, presenters, etc. |  | 6
|  | Guest hosting | Coordinate UI hosts to escort guests as needed |  | 6
|  | Set-up | Meet with UI University Support Services (USS) to review and brainstorm event set up. If off campus event meet with venue personally or via phone |  | 7
|  | Set-up | Determine needs from USS (or outside vendor or venue) and send them list of items to reserve--USS will send you a confirmation of reserved items and estimated costs--special pipe and drape, ceiling drapes, lighting, tables, chairs, staging, podium, banners, entertainment needs, etc. |  | 7
|  | Set-up | Request a diagram of the room layout (complete with tables, chairs, catering tables, bars, stage, podium, video screens, etc.) and a complete list of all reserved items from USS or event venue |  | 7
|  | Set-up | Schedule Sound, Production and Lighting (SPL) and confirm all needs for the event (meeting or via email) |  | 7
|  | Set-up | Check weather forecast to be proactive with any necessary event changes or additional steps that need to be taken to make guests comfortable |  | 7
|  | Set-up | As the last RSVP’s are coming and final numbers are being determined, confirm your final event set-up and revise diagrams if needed (determine date due with USS); provide final diagram to venue, caterer, SPL, etc. |  | 7
|  | Food & Beverage | Meet with Sodexo or off campus vendor (depending on event location) to develop proposed food and bevearge menu and review with university partners as necessary |  | 8
|  | Food & Beverage | Confirm menu; receive BEO from catering; approve BEO |  | 8
|  | Food & Beverage | If alcohol is being served, an alcohol permit must be submitted 30 days prior to event to Auxiliary Services and approved by the president's office for ALL University of Idaho Events involving alcohol--both on and off campus event. Application can be found at: https://auxiliaries.uidaho.edu/AlcoholApplications/ |  | 8
|  | Food & Beverage | If alcohol is being served discuss wristbanding protocol--i.e., will Sodexo wristband or will CMS need to be hired (USS schedules CMS) |  | 8
|  | Food & Beverage | Schedule a taste testing if applicable |  | 8
|  | Food & Beverage | Determine time catering will arrive for set up |  | 8
|  | Food & Beverage | Confirm time for food to be served |  | 8
|  | Food & Beverage | Advise catering of any special food requests (vegetarian, lactose, gluten, etc.)--and ask if slip of paper should be placed at guest seat |  | 8
|  | Food & Beverage | Provide guarantee numbers to caterer (confirm date due through BEO) |  | 8
|  | Food & Beverage | Create menu cards to identify food if buffet (Sodexo or venu generally prepares but need prompted) |  | 8
|  | Parking and Transportation | Determine parking and transportation needs (where will guests park; will transportation be provided from hotel or other location, etc.) |  | 9
|  | Parking and Transportation | If a campus event reserve parking lot(s) and consider if a lot attendant is needed for lot entry |  | 9
|  | Parking and Transportation | If off-campus event work with venue to determine available parking and advise guests |  | 9
|  | Parking and Transportation | Reserve shuttles needed for off-campus/remote parking (Vandal Trolley, golf cart, or other)--confirm pick-up and drop-off locations, timing, etc. |  | 9
|  | Parking and Transportation | Obtain parking permits, parking maps, campus maps, and written directions to provide to guests as needed |  | 9
|  | Photography and Video | Schedule Video Production to film the program |  | 10
|  | Photography and Video | Contact Photographic Services to schedule photographer |  | 10
|  | Photography and Video | Create photo list (setup, candid's, VIP's, program, etc.) and provide to photographer |  | 10
|  | Entertainment | Schedule entertainment (social, dinner, main program, dessert) as appropriate to the event. If non-UI vendor work with Purchasing and Contract Services on contract |  | 11
|  | Entertainment | Meet with entertainment and confirm their needs (stage, microphones, chairs, music stands, etc.) |  | 11
|  | Décor | If floral arrangements are needed for buffet, table centerpieces, etc., contact Sodexo or other florist vendor to shedule a meeting to discuss arrangements and budgetary guidelines |  | 12
|  | Décor | Order table linens through Sodexo or outside vendor |  | 12
|  | Décor | Consider if other elements are needed to enhance the event (candles, pipe and drape, ceiling drapes, special lighting, chair covers & bands, etc.) |  | 12
|  | Gifts and Awards | If favors/takeaways/collateral will be given to guests, work with Creative Services, UI Dept. of Trademark and Licensing, or outside vendor |  | 13
|  | Gifts and Awards | Design how awards will be displayed at the event |  | 13
|  | Gifts and Awards | Establish how gifts and awards will be handed out--wrap if appropriate |  | 13
|  | Name tags | Determine if using sticky, magnetic holders, etc. and if using stock UI format or special design for event--order supplies as necessary |  | 14
|  | Name tags | Print name tags from RSVP list |  | 14
|  | Name tags | Ask co-worker to help verify name tags against RSVP list (spelling and to make sure none were missed) |  | 14
|  | Name tags | Assemble name tags 1-2 days prior to event: name tags, table #'s, payment due (print additional as guests are added; remove cancellations) |  | 14
|  | Volunteers | If students volunteers are needed identify the needs, contact the individuals or groups to ask for their help and to hold the date on their calendar. Request that names are provided at least three days prior to event |  | 15
|  | Volunteers | When volunteer names are provided, brief volunteers on expectations via email prior to the event: arrival time, dress, role |  | 15
|  | Volunteers | Assign specific tasks for volunteer/student/staff member, create a schedule (see volunteer and staff tracking template) |  | 15
|  | Volunteers | Ask volunteers to arrive a half hour prior to start time for briefing and assignments |  | 15
|  | Seating Chart | Create seating chart template(s); organize by table, alphabetically by last name and numerically |  | 16
|  | Seating Chart | After seating assignments are drafted review with unit, leadership, etc. |  | 16
|  | Seating Chart | If using table numbers on tables ask Sodexo to provide numbers or print yourself (you will need stanchions for holding--catering has if you don't) |  | 16
|  | Seating Chart | Print place cards if assigned seating |  | 16
|  | Seating Chart | Place assigned table number on guest name tag (pre-printed and cut insert in back of name tag or label placed on back of name tag) |  | 16
|  | Branding | Coordinate items to brand the event through print materials, marketing, décor, etc. (banners, podiums, signage, logos, color scheme, name tags, etc.) |  | 17
|  | Coat Check | Reserve coat racks and hangers through venue |  | 18
|  | Coat Check | Designate coat check area and determine what that looks like (tent, tables, coat racks, number system, tip jar, etc.) |  | 18
|  | Administrative Tasks | Develop and maintain a "take list" for all supplies and event items that will be taken to event--use this list as you are packing up for event |  | 19
|  | Administrative Tasks | Develop Event Emergency Plan with event venue (office of public safety can be of assistance if needed)-- (see template) |  | 19
|  | Administrative Tasks | Develop contact list with all event university partners cell phone numbers--distribute to all partners on list prior to event (see template) |  | 19
|  | Administrative Tasks | Any contract (venue, hotel block, off campus catering, etc.) must be signed by the Office of Purchasing and Contract Services--event manager or delegates are not allowed to sign contracts. Email to: purchasing@uidaho.edu |  | 19
|  | Administrative Tasks | An Entertainment Expense Approval form must be completed and kept on file for auditing purposes; form also attached to claim voucher when paying for off campus expenses (see template) |  | 19
|  | Administrative Tasks | Place event dates on office/university calendar |  | 19
|  | Administrative Tasks | Develop an event execution schedule documenting a timeframe for all set up, rehearsals, etc. (see sample) |  | 19
|  | Administrative Tasks | Confirm all final arrangements with all vendors (campus and off-campus): rentals, linens, flowers, greenery, entertainment, a/v company, parking, facilities, etc. 1 week days prior to event |  | 19
|  | Briefing Documents | Update the event briefing document and distribute at least 7 days prior to the event to the president's office, provost, vice president for advancement, etc. as appropriate along with draft guest bios (see sample) |  | 20
|  | Briefing Documents | 1 day prior resend briefing document, final bios, and other pertinent information to president's office, provost's office, VP for advancement, etc. |  | 20
|  | Day of Event | Check all rooms and/or event locations to ensure set-up is correct, deliveries (programs, greenery, tables/chairs, etc.) have been made, work order requests have been completed, etc. |  | 21
|  | Day of Event | Test any audiovisual/lighting equipment to ensure that it’s working properly, volume levels are acceptable, etc. If on-site audio/visual technician has not been hired ensure you are familiar with the equipment |  | 21
|  | Day of Event | Check email and voicemail for any last minute RSVP changes, and update nametags and seating arrangements if necessary |  | 21
|  | Day of Event | Final set-up (break these out if desired on your final checklist): place table numbers on tables; place seating tent cards at each seat (if assigned seating); place menu cards and printed programs on tables; place directional signs if needed (restroom, coat check, balcony closed, enter here, etc.); alphabetize name tags on registration table; place favors on tables; set up coat check area (racks, hangers, number system); help florist if necessary; place script on podium; place bottled water (or pitcher with cups) under the podium for each speaker/presenter |  | 21
|  | Day of Event | If president or other UI leadership are part of the program determine if event/script/program walkthrough is needed |  | 21
|  | Day of Event | Meet volunteers/staff members assisting with the event and give them an overview of their duties: ushers, program distribution, nametag table, coat check, etc. |  | 21
|  | Day of Event | Perform scheduled walkthroughs (sound check, script read through, entertainment rehearsal) with emcees, presenters and entertainers and cover any last minute questions and make sure that they know the order of the program and they have their remarks if not already incorporated in to the script on the podium |  | 21
|  | Post-Event | Send thank you note to emcees (appreciation gifts cannot be purchased through UI budgets) |  | 22
|  | Post-Event | Thank presenters/speakers at end of evening, if possible, and within a few days with a personal note. Ask for how they thought the event went and use their feedback when planning future events |  | 22
|  | Post-Event | Thank volunteers via email or handwritten note |  | 22
|  | Post-Event | Breakdown event and make sure all event supplies are returned to their owners (supplies from your office, borrowed supplies, a/v company equipment, rental company, florist, linens, etc.). Event managers (and staff/volunteers as directed) should help with event breakdown (except catering and tables chairs if vendor is paid to do it) |  | 22
|  | Post-Event | Send survey to event attendees (if applicable) and use feedback when planning this or other future events |  | 22
|  | Post-Event | Compile all feedback on this event (including your experience) and place in file to reference when you start planning this event or future events |  | 22
|  | Post-Event | Compile a folder or binder of all printed materials (invitations, printed programs, event notes, feedback, place cards, name tags, menu cards, photos, etc. for event documentation and future reference |  | 22
|  | Post-Event | If applicable complete contact reports in Banner (AMACONT) for event attendance |  | 22
|  | Post-Event | Distribute VIP photographs to guests with a letter thanking them for attending. Can be done through email with a web link or through the mail with a print of the photo |  | 22
|  | Post-Event | Process any UI budget ticket charges. If a University of Idaho employee is paying to attend your event with a University budget number and alcohol is being served, the budget number cannot be an “X” budget. University of Idaho budgets cannot be charged sales tax. (If you charge $120 for your event then you must subtract the sales tax resulting in a charge of $113.21). Outside sales: Must charge 6% Idaho sales tax (either on top of event charge or included with event charge). Additionally, a 10% G&A fee is deducted from event revenue on outside sales (not budget transfers) |  | 22

## Contacts
Department | Contact 04/18/16 | Email
Alumni Office | Tim Helmke | thelmke@uidaho.edu
Alumni & Development Communications | Andrew Gauss | agauss@uidaho.edu
Auxiliary Services | Krista Bateman | kbateman@uidaho.edu
Campus Mail |  | campusmail@uidaho.edu
Commons/Pitman Center | Ben Aiman | baiman@uidaho.edu
Creative Services | Cindy Johnson & Emily Mowrer | cindyj@uidaho.edu; emowrer@uidaho.edu
Donor Relations | Diane Gregg & Angela Farnham | donorrelations@uidaho.edu
Emergency Management & Security Systems | Todd Perry | tperry@uidaho.edu
Executive Communications | Brian Keenan | bkeenan@uidaho.edu
Parking & Transportation Services |  | parking@uidaho.edu
Photographic Services | Joe Pallen & Melissa Hartley | photo@uidaho.edu
President's Office | Brenda Helbling, Executive Assistant | brendah@uidaho.edu
President's Office | Kevin Ketchie, Events Manager | kevink@uidaho.edu
Prospect Management & Research | Trevor Price | devres@uidaho.edu
Purchasing and Contract Services |  | purchasing@uidaho.edu
Sodexo | Jen Knerr, Ben Dewberry | catering@uidaho.edu
Sound Production and Lighting | Ben Aiman & Eric Stenback | SPL@uidaho.edu
Trademark & Licensing | Sue Smalley | sasmalley@uidaho.edu
University Support Services | Aaron Mayhugh | aaronm@uidaho.edu
Vice President, University Advancement | Ginny Boyle, Chief of Staff | boyle@uidaho.edu
Video Production Services | Jake Cutshall | jcutshal@uidaho.edu